## Strategic Plan Progress
2019 Strategic Plan Progress Report
Division of Student Affairs
West Chester University
Project Title | Project Leader | % Completed | Progress Made | Next Steps
Create a Co-Curriculuar Learning Framework | Amanda Thomas | 100% | One rubric has been created for each of the seven learning outcomes. Staff have been asked to collect data on one of nine student learning questions. Learning domains have been confirmed for all of the programs in the co-curricular catalog. | Pilot the rubrics, make adjustments as necessary.
Create Department Operations Manuals | Gerald Martin | 100% | Dean's team has created operation manuals for their areas.
Re-Establish Religious Life Council and Resources | Judy Kawamoto | 100% | Connected to religious/spiritual org advisors and student leaders in Spring 2018 to assess interest--none indicated. Re-connected again in Fall 2018, made personal connections at Involvement Fair. E-mailed student leaders and advisors to assess interest; very low response rate, little interest indicated in this initiative. Can re-visit the concept in 2019 - 2020 academic year.
Initiate Community Service Projects for Sports Clubs | Eric Maki | 100% | Campus Recreation has parternered with Chester County Intermediate Unit to host two programs per week throughout the months of October, November, December, February, March and April. Instructional experiences have included Ultimate Frisbee, Nutrition, Cycle Class, and Lacrosse. | Continue this experience for fiscal year 2020 and beyond. Expand to encompass additional sport club activities.
Evaluate Student Affairs Involvement in First Year Student Summer Programs | Judy Kawamoto | 100% | Connected with ADP/Summer Bridge colleagues to assess need, coordinated Student Affairs participation. Implemented new Campus Rec programs for participants. | Review changes that were made and determine how to proceed next year.
Build Faculty and Staff Capacity Regarding Violence Prevention | Alicia Hahn-Murphy | 100% | 31 faculty and staff attended the Capacity Building on December 17. | Those interested in engaging in violence prevention will come back together to fulfill items identifed in the strategic planning session.
Design a Co-Curricular Program Catalog | Amanda Thomas | 90% | Created draft of student success maps for Health and Wellmess, Leadership, Social Justice, Community Engagement, and Career Readiness. First draft of the Co-Curricular Programs website has been created along with the first version of the marketing plan. | Add the program formats and program levels to the program descriptions. Launch the catalog website.
Create a Four-Year Educational Map/Curriculum | Amanda Thomas | 90% | Idenified the list of educational programs that occur on a regular, sustained basis, determined the learning outcomes they address and when we would suggest students participate in these programs. | Explore visual designs for the maps, finalize the maps, conduct a gap analysis at a later point in time.
Revise the Fraternity and Sorority Recruitment Process | Cara Jenkins-Sullivan | 80% | Significant increase in students joining via deferred recruitment. Will not hold sorority recruitment prior to classes starting in january again due to financial impact of meals and housing. | Conduct a formal assessment
Expand the Student Wellness Framework to Incorporate Multiple Identities | Sherry Mendez | 80% | Framework has been expanded by expanding the Dimensions of Wellness Model. | Focusing on program development and implementation
Partner with Students to Provide Health Programs to Residential Students | Marion McKinney | 70% | Faculty, staff and students are involved. The studio is up and running. | Expand program to be offered after hours.
Increase Engagement and Positive Messaging in Our Community | Sandy Jones | 70% | Websited developed. Outreach during community parades (Halloween and Christmas) with information and linkage to OCCS and WCU Cultural Affairs. Student film race to be launched on April 4 with films show during RAMboree spring event.
Enhance the First Destination Report | Jennifer Rossi Long | 70% | Data is being cleaned. A communications plan has been drafted for sharing the report with the campus community. Talked with the marketing and communications team about creating an interactive dashboard. | Work with university marketing to create summary and college marketing reports that are visually appealing. Obtain approval for the communications plan and begin to roll it out.
Develop a Comprehensive Plan to Support First Generation Students and Families | Judy Kawamoto | 70% | Planning committee formed; West Chester's First logo developed; kick-off event held August 22, plus additional 7 programs over the course of the semester. Website developed. Benchmarked with 73 schools, data will inform future initiatives. New structure with five subcommittees (Programs, Living-Learning Community, Academics, Mentoring, Communication) to be implemented in Spring 2019. Immersion program for New Students and First Generation completed in August, 2018. One weekend trip filled with a total of 10 participants. | Increased marketing and exposure to 1st Generation and New Students prior to, during, and post-orientation programs
Enhance the Healthy Lifestyle Education Program | Eric Maki | 70% | Expanded Lifestyle Nutrition educational offerings through Wellness Wednesday programs. These programs are occuring from 7-9PM throughout the spring semester. Collaborations include students from the Nutrition adn Dietetics academic program who instruct portions of these educational sessions. | Hire a full-time graduate assistant for fiscal year 2020 and expand the program.
Improve Mental Health Support for Athletes | Julie Perone | 70% | All student athletes were screened for mental health concerns in the fall as part of their preparticipation exams. Referrals were made based on the results of the mental health screen. Continued outreach and programming around mental health conducted with student athletes. | Continue to improve the mental health screening. Develop student athlete support group.
Improve Campus Influenza Education and Prevention | Robyn Spragins | 70% | Promotion of vaccination with website, during clinic appointments, and digital signage. Student learning outcome survey conducted post immunization at campus clinics. | Consider steps to address student misconceptions about flu vaccination. Addition of open-ended questions fo flu vaccine survey to further assess student learning as a result of flu immunization programs,
Promote URM Student Connections | Judy Kawamoto | 70% | Diversity Breakfast participation did not increase over the past two years (n=18-19 per year). Changed the name of the program to the Inclusive Career Connections Breakfast. Exploring a collaboration with the LADMC next year for a program called "Resumes on the Run." Diversity Breakfast participation did not increase over the past two years (n=18-19 per year). Changed the name of the program to the Inclusive Career Connections Breakfast. | Exploring a collaboration with the LADMC next year for a program called "Resumes on the Run."
Leverage Technology to Maximize Internship and Employment Opportunities | Jennifer Rossi Long | 70% | Handshake contract has been signed; implementation has begun; exploring the possibility of leveraging LinkedIn and CareerShift to source employers for potential recruiting partnerships. | Pull data from our old system and transfer it to Handshake, customize Handshake, conduct training and work on single sign on and data migration with IS&T. A full launch to students and employers is expected by July 1.
Educate the WCU Community about the Student Conduct Process | Chris Brenner | 60% | Created group process web page with flow chart, complied with new PA Hazing law and distributed link to other partner pages for posting/linking. | Working on clarifiying the notice letter that initially goes to students and working with orientation program to continue to be proactive.
Expand Outreach Efforts to Off Campus and Commuter Students | Sandy Jones | 60% | Groups established at August orientation and January orientation. Focus groups and/or assessment with first year commuters to be completed in spring 2019.
Implement Livestream for Student Affairs Events | Sabrina Rightmer | 60% | Meet with IS&T staff to discuss colloboration potential and was told DMC cannot absorb any of this iniaitive. IS&T staff recommended to us the creation of a FT position to coordinate this work in our department. Athletics is investigating new technology for Hollinger which will help us stream volleyball and basketball with limited staff requirements. Did stream 45 events in the Fall 2018, which is 31 more than what the PSAC required for this fall. | Will meet with Seth Birch to see how they livestream Arts events.
Implement a Procedure for Scheduling Programs in Advance | Sabrina Rightmer | 60% | Shared the spring program calendar at the winter directors retreat.
Strengthen Suicide Prevention Efforts | Julie Perone | 60% | Students continue to use this interactive, online, and anonymous program to learn about Counseling Center services and to get connected with the Counseling Center. | Continue to use this program as a way to connect at-risk students to mental health services.
Evaluate the Implementation of Internal Alcohol and Drug Sanctions | Sherry Mendez | 60% | Reviewed current practices, and was waiting for new AD to start. Search failed and will be unable to complete until position is filled. | Postion will be reposted spring semester.
Review the Divisional Organizational Structure | Senior Leadership Team | 60% | Executive Director, Senior Director, Assistant Director of Compliance, Associate Director of Sykes Student Union positions have been posted and interviews are completed. Additional Assistant and Associate Director searches are beginning. | Post Facilities and Operations Manager position for Athletics.
Develop a Plan to Renovate Sykes Student Union | Dave Timmann | 50% | A feasibility study was conducted in the spring of 2018 to address growing facility needs. The results of the study are on hold and focus has changed to looking at the facility exterior to enhance curb appeal and functionality. | Stand-alone projects are scheduled for the summer of 2019; roof replacement, restroom upgrade, Ballroom acoustic and aesthetic improvements
Design a Living Learning Community | Gerald Martin | 50% | The failed search for the Associate Director has delayed the development process. But a consultant did come in to educate the staff on developing the LLCs. | Hire the Associate Dierctor. This project will be restarted upon the Associate Director hire. Thus it is unlikely to be completed in fiscal year 2019.
Evaluate the Recognition Model for New Student Clubs and Organizations | Gerald Martin | 50% | We will meeting this term to complete the model. | Draft model is underway.
Pilot Co-Curricular Paths and a Co-Curricular Transcript | Judy Kawamoto | 50% | RFP completed to identify new technology platform (Campus Groups), submission form for transcript component is created and data collection will be completed by April 1, curriculum review committee is being formed, continuing to develop technology component (waiting for a response from IS&T), marketing survey in development. | Gather, review and approve information for transcriptable programs, establish the API for connecting Campus Groups and PeopleSoft, gather feedback from students on marketing the transcript.
Re-apply for the Carnegie Community Engagement Reclassification | Sara Hinkle | 50% | The committee has been meeting throughout the year and is on target to have a draft compiled by early February in order to make the April 15 deadline.
Create a Partnership with the Higher Education Policy and Student Affairs graduate program | Sara Hinkle | 50% | This goal is an ongoing one. Last year we created the first annual HEPSA Interview Day and we are planning the second one for March 22, 2019.
Increase Awareness of Initiatives to Reduce Student Alcohol Issues in the Community | Sara Hinkle | 50% | To accomplish this, we have engaged in such initiatives as the 2nd annual Church St. Fest, and providing food for this event and our upcoming Ramboree. The CCC work has been slow, and the mayor recently asked to hit pause on this initiative.
Create a Student Affairs Staff Development Plan | Sara Hinkle | 50% | The following initiaves have been implemented over the past semester: the infusion of staff development into our DOSA meetings, new staff onboarding, support staff meetings, Lunch and Learns, and $5 Fridays.
Increase Parent and Family Engagement in Promoting Student Success | Sara Hinkle | 50% | Last semester we created a parent and family newsletter, Ram Fam Monthly. A director of Parent and Family programs has recently been hired.
Create Social Justice Programming for Women | Alicia Hahn-Murphy | 50% | 5 programs facilitated on main campus; 1 facilitated on the Philadelphia campus
Improve Physical Space and Infrastructure | Pete Galloway | 50% | Student Recreation Center redesign project completed over Semester Break 2018/19; planning continues to renovate Baseball and Softball complexes Summer 2019; work to begin soon to create new Weight Room in Ehinger and creation of new Basketball locker rooms in Hollinger; renovations to the Dowdy Multicultural Center were completed over Semester Break 2018/2019, renovations to the Lawrence 202 Office Suite were completed over Semester Break 2018/2019 | Completion of Baseball and Softball complexes in Summer/Fall 2019; creation of Weight Room in Spring 2019 and Locker Rooms in Summer 2019; Cara to schedule meeting to begin housing and space feasibility study Spring 2019.
Strengthen the Student Affairs Assessment Infrastructure | Amanda Thomas | 40% | Website has been redesigned to be more user-friendly and provide more content. LDMC and CWGE pilot of the visitor management system has been successful, LDMC has had approximately 1,200 visits from 8/28 to 12/3. CWGe has had 23 visitors from 8/27 to 11/14. Five student learning rubrics have been created to support staff in program development and assessment.
Expand Student Athlete Support Services | Terry Beattie | 40% | Spent fall semester accessing the current program. A sub-committee of our Student Athlete Advisory Committee was formed to assist in this process. Discussions with program facilitators have also occurred to gauge where improvement and expansion can occur.
Create a Four Year Residence Education Curriculum | Marion McKinney | 30% | On hold. | Associate Director to be hired who will spearhead this effort.
Initiate Off-Campus Living Education Program | Sandy Jones | 30% | Hosted Off Campus Housing Fair with local property owners, codes enforcement officers and Places4Students housing platform. In February 2019 Rambassasdors will host Moving Off Campus programs for resident students in cooperation with resident staff. Online Off Campus Education series will be launched by April 2019 for education of students living and/or moving off campus with support from local property owners.
Increase Outreach, Support, Services and Programming for Multicultural Students | Judy Kawamoto | 30% | Will submit proposal to NSP for the LADMC to present a breakout session for Orientation Summer Dates in June; GA/Intern are currently working on a recruitment plan that will be launched the first week of March - to help diversify our candidate pool for the PM position; Carnival location has been confirmed for Aug date - pending confirmation from MOAB Orgs who will host a table; LADMC evaluation will launch at the end of February. | Meeting with NSP Staff to discuss breakout session for Orientation; GA/Intern will lauch PM Application first week of March - recruitment plan: target specific colleges, contact prior mentees, host info sessions, post flyers, speak at MOAB organizations; confirm MOAB orgs for tables (LADMC Carnival) ; review LADMC evaluation results with new senior director once they are hired.
Integrate Service Learning into the First Year Experience | Service-Learning and Volunteer Programs Senior Director (TBD) | 30% | Fall 2019 Integration Plan developed by Kate Colyer and Service-Learning Faculty Associate Katie Solic. Plan was reviewed and discussed in January 2019 with CAPC, faculty leads for FYE, and Judy Kawamoto. | February 2019: One FYE Faculty teaching team will be identified to pilot this integration plan for Fall 2019. March - May 2019: Service-Learning Faculty Associate will provide consultation and support to teaching team to prepare for Fall 2019 (i.e. pedogoical design, community partnership development, etc.) June - August 2019: OSLVP Associate Director will support final stages of preparation for integration (i.e. risk management, parntership development, etc.)
Reduce Financial Barriers to Student Degree Completion | Service-Learning and Volunteer Programs Senior Director (TBD) | 30% | Held a strategic planning retreat with Resource Pantry Advisory Board in January to explore various strategies to ensure the sustainability of the Pantry in alignment with its mission and vision. | Spring 2019: Develop a vision that refelects supporting the holistic needs of students to guide future action steps and processes in the Pantry (i.e. case management via MSW program, etc.) Additionally, work with WCU Foundation to apply for grants and meet with potential donors to secure additional funding.
Create a Wellness Network | Sherry Mendez | 30% | Establishment of network started, and data from members collected. Progress slowed due to resignation of co-chair and other staffing changes. | After co-chair searches complete regroup and establish meetings
Enhance Outreach and Programming for the LGBTQA Community | Tiffany Gray | 30% | Facilitated a Culturally Queer training and intentional outreach/communication regarding promotion of events. Currently planning a 3 hour RAMping It Up: Trans and Queer Advocacy training for March. | Continue to work togehter regarding promoting events and offering training opportunities for students.
Expand LGBTQA Resources for Students | Tiffany Gray | 30% | Continue to include the Philly campus when sending out program details and information. Make sure they have our flyers for promotion. | Continue to be intentional about the types of resources that could extend to the Philly campus beyond our trainings such as; LGBTQIA+ friendly providers lists, health care supplies, "swag" related to LGBTQIA+ support and solidarity etc (pride flags, buttons, stickers, flyers...)
Promote Environmental Sustainability | Pete Galloway | 30% | Graduate Assistant for Sustainability conducted a residence hall waste audit in fall and shared results with the campus via a report and a presentation; research has been done around the design of a Sustainability Living Learning Community; the Ride Amigos program (ride sharing) began this fall; the new Aramark contract includes support for the Resource Pantry, which began this fall. | Planning continues to begin a Sustainability Peer Education program Fall 2019; staff will dedicate time to promote the Ride Amigos program to increase registration and use; development of additional sources of food and financial resources for the Pantry will occur.
Align Sanction Requirements with the New Student Affairs Learning Outcomes | Chris Brenner | 20% | Graduate student has begun to link these sanctions and learning outcomes. Will be able to make progress having learning outcome rubrics. | Use rubrics to complete.
Extend Outreach Efforts to Transfer Students | Sandy Jones | 20% | Assistant director position filled in Dec '18; priorities re-focused with outreach to transfer students in late spring and/or early summer. | Change orientation based on priorities.
Create a Comprehensive Student Affairs Communications and Marketing Plan | Sabrina Rightmer | 20%
Create a Student Affairs Development/Fundraising Plan and Resources | Sara Hinkle | 20% | A few things are currently in the works here: collecting potentially fundraising iniatives from departments; creating a more systematic way to distribute the Student Leadership Development Funds; and providing resources to staff regarding alternative funding sources.
Establish a Collegiate Recovery Community and Programs | Sherry Mendez | 20% | Met with Residence Life and Housing regarding space. Also met with Dr. Davenport to discuss financial needs including staffing. Agreed that for the time being the new AOD AD and other Wellness staff will assume leadership role for the CRC. AD search failed in Dec. | Repost for AD position during spring semester. Continue meeting as a collective, and meet with Residence Life and Housing to lock space options.
Expand Crisis Resources and Training | Tony Delgado | 20% | Finalized student death protocol; determining remaining scope of the project; rough draft of CARE team manual (outline) is underway. | Complete draft of CARE manual; create student and employee training; develop marketing strategies to promote at WCU.
Create Online Support Programs and Resources | Amanda Thomas | 10% | Not progress during this period.
Study the Impact of Co-Curricular Programs and Services | Amanda Thomas | 10% | LDMC and CWGE office visitor data is being collected in an effort to determine who participates in co-curricular programs and services. A new contract has been signed to bring on a new community engagement platform that will make it easier to track program attendance.
Increase Options to Meet Student Conduct Sanction Requirements | Chris Brenner | 10%
Re-imagine Housing Space to Maximize Occupancy | Sue Visoskas | 10% | During Fall 2018, held meeting with Facilities colleagues to look at lounge furnishings to support shared spaces for students to use. This will allow us to look at tripling more student bedrooms, as they will have other spaces within the halls to gather and socialize. | Prepare materials to seek approval from West Chester Borough to offer triples to students as an option.
Revise the Sexual Misconduct Infrastructure | Tony Delgado | 10%
Prepare the Sciences and Engineering Center and Commons for Opening | Pete Galloway | 10% | Planning meetings with campus team continue; first meeting held to engage current Aramark staff on plans for building. | Meetings will be ongoing; refine the design and major equipment list as necessaary; will begin to identify items that will need to be purchased that are not part of the construction budget.
Conduct a Division-wide Self Study and External Review | Amanda Thomas | 10% | Benchmarking divisionwide review practices and processes. | Finalize the process, practices and timelines; convene a group to work on the self-study; identify external reviewers.
Engage the Campus Community in Developing Ideas to Improve West Chester University | Amanda Thomas | 0% | On hold
Develop a Comprehensive Fraternity/Sorority Advising Model | Cara Jenkins-Sullivan | 0% | Consider changing due date to 2020 | Meet with SLI team to discuss current faculty/staff advising issue
Implement a Holistic Student Development Model for Fraternity and Sorority Members | Cara Jenkins-Sullivan | 0% | No work has been done in this area | Create summer planning outline
Enhance Community Connections to the Sykes Student Union | Dave Timmann | 0%
Create Deeper Connections between Students and Student Affairs Staff | Marion McKinney | 0% |  | Need to hire an associate director before we can begin this project.
Create a Physical Environment that Reinforces Learning and Our Values | Marion McKinney | 0% |  | Need to hire an associate director before we can begin this project.
Collaborate with Academic Affairs on Pathway Certificates | Service-Learning and Volunteer Programs Senior Director (TBD) | 0% | Awaiting information from CAPC about next steps regarding how courses will be designated as part of the Community Engagement Pathway and when the initiative will be launched.
Leverage Spending through the Coordination of Division Purchases | Executive Director of Finance | 0% | On hold | Hire new Executive Director
Reduce Rollover to Plant Fund | Executive Director of Finance | 0% | On hold | Hire new Executive Director
Review and Revise the Student Affairs Budget Process | Executive Director of Finance | 0% | On hold | Hire new Executive Director
Integrate Social Justice into Sanctions, Programs and Trainings | Chris Brenner | 0% | Recently re-assigned to Chris Brenner. | Create a plan over Summer 2019.
Create a Student Affairs Diversity Plan | Sara Hinkle |  | Building the staff development plan. Other components are on hold until we receive more direction from Diversity, Equity and Inclusion.
Provide Paraprofessional Training Opportunities | Sara Hinkle |  | Checking with staff in the division.